## Issues Tracking
# | Description | Type | dependency | who | Status | notes
1 | There are 3 states on sorting... asc, desc and none.. however, none doesnt get it back to original state | GUI | no | Andrey | FIXED | ANDREY/GUI BRANCH
2 | sorting state is not valid after search | GUI | no | Andrey | FIXED | ANDREY/GUI BRANCH
3 | I can drag the column off the screen it expends the horisontal bar infinitely. | GUI | no | Andrey | FIXED | ANDREY/GUI BRANCH
4 | enter key doesnt work for search clear ( X)... example if i enter value in search field and do tab tab enter... search field wont clear, i have to click in order to clear | GUI | no | Andrey | FIXED | ANDREY/GUI BRANCH
5 | arrows dont work for navigation | GUI | no | Andrey | FIXED | ANDREY/GUI BRANCH
6 | if several files are open at once, search doesn’t seem to work | GUI | no | Andrey | FIXED | ANDREY/GUI BRANCH
7 | Return column by default is too small to show its title | GUI | no | Andrey | FIXED | ANDREY/GUI BRANCH
8 | Selecting text is disabled | GUI | no | Andrey | FIXED | ANDREY/GUI BRANCH
9 | Mismatch of Structs to OpCodes | Mapping | yes | josh | FIXED
10 | display parsed flag names | Gui | yes | Andrey | FIXED
11 | display parsed error names | GUI | yes | Andrey | FIXED
12 | raw byte buffer | GUI | yes | Andrey | DONE
13 | Filtering - using toggle buttons | GUI | no? | Robbie | DONE | ANDREY/GUI BRANCH
14 | display time stamp | GUI | yes | Dustin | FIXED | ANDREY/GUI BRANCH
17 | parsing of flags in header file | GUI | no? | Andrey | FIXED
18 | parsing of error codes in header file | backend | no | Andrew W | DONE | MASTER
20 | parsing of time stamp | backend | no | Andrew W | DONE | MASTER
21 | discrepancies between header files | backend | no | Andrew W | Done | 2/14 -- still several errors in mapping file (namely stuff that's larger than 16 byte command structs)
22 | exceptions on good structs | backend | no? | Josh | FIXED | Generic AQ
23 | #defines mapped | backend | yes | Andrew w | done
24 | parsing of error codes in log file | backend | no | Andrew W | DONE | MASTER
25 | parsing of flags in log file. | backend | no | Steve | FIXED | ANDREY/GUI BRANCH
26 | parsing of lancof | backend | no | andrew q | NOT VALID | Per Anderw W > closing due to not being a valid issue
27 | total amounts of in file or in search | GUI | no | dustin | FIXED | ANDREY/GUI BRANCH
28 | raw byte buffer returns nothing | backend | no | steve | FIXED
29 | flag hovering to flag name | GUI | yes | Andrey | FIXED
30 | Check junk filter | backend | no | Andrew Q | IMPLEMENTED | naive approach was fine due to steve's regexes...
31 | parsing of fail_update | backend | no | Andrew Q | IMPLEMENTED
32 | Thread file opening | GUI |  | Andrey | FIXED | ANDREY/GUI BRANCH
33 | Loading bar for file opening | GUI |  | Andrey | FIXED | ANDREY/GUI BRANCH
34 | File>Options window purpose? it seems it doesnt do anything... ok button is hidden behind the frame by degault | GUI |  |  | FIXED | ANDREY/GUI BRANCH
35 | Sorting by "#" numbers are not in asc order | GUI |  |  | FIXED | ANDREY/GUI BRANCH
36 | line numbers dont correspond to the raw file ( off by 1 line) | backend |  |  | NOT VALID | ANDREY/GUI BRANCH
37 | flash_update_fail.log & lanconf.log wont open | backend |  |  | FIXED | ANDREY/GUI BRANCH | see issue 26.. lan_conf is not a valid file
38 | I can type in right bottom frame? Please lock it... | GUI |  |  | FIXED | ANDREY/GUI BRANCH
39 | mismatch of mapping vs. struct header parser | backend |  |  | FIXED | MASTER
40 | show friendly error message if cant open the file | GUI |  |  | FIXED | ANDREY/GUI BRANCH
41 | Timestamp column displays orphaned entries when searching | GUI |  |  | FIXED
42 | Cant select a row using flags column ( or its really slow and laggy) | GUI |  |  | FIXED | ANDREY/GUI BRANCH
43 | If i maximize window, than restore.. flags column does not display accurately | GUI |  |  | FIXED | ANDREY/GUI BRANCH
44 | Copy row vs copy cell on flags column gives different results | GUI |  |  | NOT FIXED | i dont know if we care about this one
45 | Cant filter and search within filtered content | GUI |  |  | FIXED
46 | After resizing columns if the second file is opened.. op code column takes the whole screen | GUI |  |  | FIXED | ANDREY/GUI BRANCH
47 | Automatically switch to new tab when a file is opened | GUI |  | Robbie | FIXED | ANDREY/GUI BRANCH
48 | Flags ... performing bitwise AND, different results...(this is a question) | GUI |  |  | FIXED | ANDREY/GUI BRANCH
49 | Log parser doesnt parse to right op code | backend |  |  | FIXED | ANDREY/GUI BRANCH
50 | search doesnt work on line numbers | GUI |  |  | FIXED | ANDREY/GUI BRANCH
51 | sorting by flags... inconsistent | GUI |  |  | Done
52 | for file "flash_udpate_fail.log" since timestamp is missing.. GUI should not display -1.-1 | GUI |  |  | FIXED
53 | Page UP and Page down, holding arrowDown .. crashes the app | GUI |  |  | FIXED | invalid record actually causing the crash not the key( see issue 54)
54 | certain recrods throw exception into GUI ( example line 889 in normal_trace_syslog file) | backend |  |  | FIXED | MASTER
55 | Cant search by flag names | GUI |  |  | FIXED | not going be fixed
56 | when we display field values... bit value displayed is different than in logs.. exampe: log(normal_trace..) file at line 162show param (0,1) 0x000052E4 0x0000892B.... GUI displays these values as E4 52 00 00 and 2B 89 00 00 .. | backend |  |  | FIXED | little endian vs big endian
57 | when timestamp column is missing.. an extra column appears on the right ( see issue 52) | GUI |  |  | FIXED | this is a feature not a bug
58 | Displaying opcode for UNKNOWN is invalid (Example GUI displays opcode 0xFFFFFF03 when the actual opcode is 0xFF03) | GUI |  |  | FIXED
59 | No processsing logs being created by the app | backend |  |  | NOT FIXED | stretch goal?
60 | writeback column is too small by default ( the header is not readable) | GUI |  |  | FIXED
61 | Limit search bar to 255 char? this is a wish list | GUI |  |  | Fixed/kinda | wish list
62 | if no row selected and I do right click on the header row... the menu(copy row/copy cell) simply sticks.. | GUI |  |  | fixed
63 | when i close the file.. events total wont clear | GUI |  |  | fixed
64 | Soting by Filed Name and Filed Value.. not the same behavior as the rest of the app sorting.. ( 3rd stage (unsorted) should bring back original state) | GUI |  |  | fixed | minor
65 | Once i collapse the bottom frame.. i cannot bring it back up | GUI |  |  | FIXED
66 | It needs a pronounceable name | GUI | 1 |  | FIXED | Andrey shortened the name to AdminQ Viewer
67 | When field data is a u16 or u32, it would be nice to print that value rather (or maybe in addition to?) the raw byte | Backend/gui | 2 | andrew w/andrey | FIXED
68 | The datalen value would be useful to have printed somewhere, possibly over the lower right data buffer pane | GUI | 3 |  | FIXED | see issue # 80
69 | I’m seeing incorrect values in the data buffer pane. For example, looking in the flash_update_fail.log that I send you, the data for the first nvm_read (line 13294) shows as “8600 0000”, but the logfile shows “00008086 00000000”. The following writeback buffer is shown as “8000 0000” but the logfile shows “00007D80 00000000”. | backend | 4 | steve | FIXED
70 | There is a set of data messages that are a little different than the request and response messages, and they need to be indicated in the UI somehow. for example, starting on line 41734 of the flash_update_fail.log, there is the 0x0703 request, followed by the writeback on line 41741; note that those are started by an “AQTX” tag. These two are followed by another 0x0703, but this is tagged with “AQRX”: this is an asynchronous event message that needs to be identified differently. | gui/backend | 5 | andrey/andrew w | ALMOST | see issue 82
71 | The sorting of the columns seems backwards to me – the arrow should be pointing in the direction of the increasing values. When the file is first loaded, the lines are in their temporal order as expected, but the arrow is pointing up – I would expect it to be pointing down | GUI | 6 |  | NOT FIXED | looks like we are not going to do this one.
72 | When sorting the Opcode column, please sort by opcode value, not name. | GUI | 7 |  | FIXED
73 | In the Op Code view, for convenience and consistency with our internal documentation and code, please display this with leading to fill 4 columns. For example, I would write the printf spec as “0x%04x”. This might actually help with the sorting issue if this is put at the beginning of the field rather than at the end. | GUI | 8 |  | FIXED
74 | Looking at the file normal_trace_dmesg.log, the field names and values shown for opcode “UNKNOWN – 0x205” change from entry to entry. Perhaps a previous decoding is being used? If the opcode and decoding is not known, then we should see the default fields cookie, param1, param2, addr_high and addr_low. | backend | 9 | andrew w | FIXED
75 | Looking at the file normal_trace_dmesg.log sorted by opcode, stepping through each of the 0x211 lines shows data fields of several different layouts. I suspect that the order of lines displayed in the GUI is being used to directly index the database and getting the wrong data. | gui | 10 | andrey | andrey said fixed please check
76 | I think I didn’t point out to you that there are several different devices that print at the same time into the log, and we need to be able to separate out these conversations. This is easiest to see in the file normal_trace_dmesg.log. Note that each line has something like “i40e 00.0” or “i40e 00.1” or “i40e 00.3” in the prefix? This number is a device ID number.If we can add another column in the UI to display this device id, I believe we then could filter out the ones we want to see at any particular time.Be aware that sometime in the future, this number “00.3” format will probably change to the full PCI device ID spec seen elsewhere in this form: 0000:24:00.3. | backend/gui | 11 | andrey/andrew w |  | REYNOLDS/NEWGUI
77 | When opening the File¦Open dialog to find a second file, it should open in the same folder that I found the first file. | GUI | 12 |  | FIXED | ANDREY/GUI BRANCH
78 | Is it possible to add a Drag/Drop so I can find the file in the Window file explorer and drag it into the Viewer? | GUI | 13 |  | Fixed | ANDREY/GUI BRANCH
79 | I like the flexibility of the panes and the columns, except for in the data buffer view. The data buffer view should always show lines only 16 bytes (well, okay, maybe 32 bytes, but either one of the other), with only the last line shorter if the data isn’t a multiple of 16 (or 32) bytes. That might mean needing a horizontal scrollbar. | gui | 14 |  | FIXED SERGE CHECK | more testing needed once backend fixes buffer issues/ andrey fixed pleas update status
80 | buffer line counter is not displaying correct value | GUI |  |  | FIXED/Kinda | we assume the counter always starts with 0.. its not always true
81 | Display device ID | GUI |  |  | FIXED | see issue 76
82 | due to log file being incosistent we are not parsing all commands properly ( see question to shannon PDF) | backend |  |  | NOT FIXED | decided not to fix it
83 | search for line numbers are inconsistent the search by line tops out at 40000+ so if i search for a value 25360 it works.. but when i search 44040 nothing shows up.. althouh there is such a line | GUI |  |  | FIXED
84 | Incrementing buffer counter by 20 vs 10? | GUI |  |  | FIXED
85 | Search doesnt work for async or device Id fields | GUI |  |  | FIXED

## GUI Tests
# | Step | Status | Issue
1 | Minimize button | PASS
2 | Maximize button | PASS
3 | Close button | PASS
4 | Close icon on the tab | PASS
5 | Window-drag | PASS
6 | Window double click - expand | PASS
7 | Sort: Op Code | PASS | 1,2
8 | Sort: Flags | PASS | 1,2
9 | Sort: Error | PASS | 1,2
10 | Sort: Return | PASS | 1,2
11 | Search: op Code | PASS
12 | Search: Flags | PASS
13 | Search: Error | PASS
14 | Search: return | PASS
15 | Search Button Click | PASS
16 | Clear button Click | PASS
17 | File Menu Click | PASS
18 | Right Mouse click | PASS
19 | Double Click | PASS
20 | Record Selection Click | PASS
21 | Arrows Key | PASS
22 | Tab Key | PASS
23 | Esc Key | PASS
24 | Enter Key | PASS
25 | Open Muplitple Files | PASS
26 | Search with mutiple files open | PASS
27 | Drag-n-drop | PASS
28 | Resolution | PASS
29 | Column Resizing | PASS
30 | Buffer size
31 | Value/Key mapping
32 | Flags ( sorting, display)
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190